## Work Plan
Resupply Work Plan
Redesigned in Excel from the provided image with cleaner formatting and preserved task details.
Activity | Description | Person Responsible | Frequency | Timeline | Remarks
Output 1 | Old A/R update calculated till 31-Mar-2026
1.1 | Generate list of A/R submitted to insurances on a daily basis and send report to management. | M. Tufail | Daily | Daily | Daily progress of A/R submissions.
1.2 | Follow up submitted A/R and report daily to management. |  |  |  | Follow up submitted A/R with insurance companies by call, email, or fax.
Output 2 | New A/R generated after 1-Apr-2026
2.1 | Generate list of A/R submitted to insurances on a daily basis and send report to management. | M. Tufail | Daily | Daily | Daily progress of A/R submissions.
2.2 | Follow up submitted A/R and report daily to management. | M. Tufail | Daily | Daily | Follow up submitted A/R with insurance companies by call, email, or fax.
Output 3 | Patient Responsibility
3.1 | Generate patient responsibility list through 31-Mar-2026 and obtain guidelines from Alessandra for communicating with patients. | Arslan & Qamar | Daily | Daily | Keep the list updated through 31-Mar-2026 as a separate record.
3.2 | Generate the new patient responsibility list from 1-Apr-2026 onward and update it daily. | Arslan & Qamar | Daily | Daily | Take detailed communication guidelines from Alessandra.
Output 4 | Develop SOPs for verifications
4.1 | Prepare a list of all verifications required for resupply along with monthly cost. | Arslan & Qamar | Once | Once | One-time setup activity.
4.2 | Document the prior authorization required for resupply and write procedure plus SOPs for PA. | Arslan & Qamar | Once | Once | SOPs required.
4.3 | Define all methods and procedures to contact customers for May 2026 resupply, categorized by Retail and Insurance. | Arslan & Qamar |  |  | SOPs required.
Output 5 | Development of resupply business model
5.1 | Create the active list of resupply patients. | Imran
5.2 | Prepare the May 2026 resupply demand based on insurance rules. | Imran
5.3 | Prepare SOPs and the model for fulfilling patient resupply orders. | Imran |  |  | Include order intake, demand to vendor, payment from customer, and item delivery.
Output 6 | Financial model for resupply business
6.1 | Document monthly and annual expenses required to run the business.
6.2 | Document current payables.
6.3 | Build the revenue model based on A/R, resupply sales, and liquidation of assets. |  |  |  | Model scenarios: excellent, good, and worse.
6.4 | Prepare the final model that covers all above components.