WorkPlan

Transcribed from the provided image; one phrase in item 2.8 is unclear and is marked accordingly.

| Task | Activity | Responsible | Timeline |
| --- | --- | --- | --- |
| 1.1 | A/R update on daily basis, to be submitted at the end of day. Ins only. | M. Tufail | Daily & weekly |
| 1.2 | Patient Responsibility (support by Arslan/Qamar) | Alessandra | Weekly |
| 1.3 | HOSPICE Follow Up. | Alessandra | Weekly |
| 2.1 | ALL types of verifications and eligibilities resources required in resupply with cost. /DA | Arslan | 24-Apr-26 |
| 2.2 | Re supply customers coverage. Active patient list | Imran | 24-Apr-26 |
| 2.3 | May 2026 resupply items eligibility of private insurances | Imran | 24-Apr-26 |
| 2.4 | How many ways and procedure to contact customer for resupply in May-2026. Categorize (Retail & Ins.) | Arslan | 24-Apr-26 |
| 2.5 | Order placed by patients in response of (2.4). | Arslan & Qamar | 24-Apr-26 |
| 2.6 | How to deliver items. Purchase & dropship and confirmation & payment receipt in case of retail. | Imran & Ghulam S. | 24-Apr-26 |
| 2.7 | Complete model will be developed for 2.6. | do | do |
| 2.8 | Communicating with patient to share [unclear] current business status. (Brochure & ads) | do | do |